## Process Steps and Stakeholder R
Process Steps and Stakeholder Register
The high-level process steps for the SIPOC plus the stakeholder register to score for influence/interest and assign RACI.
Lab 6 · Certified Lean Six Sigma Green Belt (CLSSGB) Training · TGS-2025055775 · Version v5
Stakeholder | Role | Department | Influence (1-5) | Interest (1-5) | Current Stance
Distribution Manager | Sponsor | Distribution | 5 | 5 | Supportive
Pick Supervisor | Process owner | Warehouse | 4 | 5 | Supportive
Despatch Lead | Process owner | Despatch | 4 | 4 | Neutral
WMS Analyst | Subject expert | IT | 3 | 3 | Neutral
Carrier Liaison | Interface owner | Logistics | 3 | 4 | Neutral
Night Shift Lead | Frontline | Warehouse | 2 | 5 | Sceptical
Customer Service Manager | Voice of customer | Service | 3 | 5 | Supportive
Finance Controller | Benefit validator | Finance | 4 | 2 | Sceptical
Inbound Supervisor | Upstream supplier | Goods-in | 2 | 3 | Neutral
Notes
• Plot influence against interest to decide who to Manage Closely, Keep Satisfied, Keep Informed or Monitor.
• Exactly ONE person may be Accountable (A) for each process step in your RACI.