## Project Charter Inputs
Project Charter Inputs
The agreed facts and figures to drop into the project charter — baseline, target, financials, team and milestones.
Lab 5 · Certified Lean Six Sigma Green Belt (CLSSGB) Training · TGS-2025055775 · Version v5
Charter Element | Value
Process | Order fulfilment: order release to carrier handover
Baseline late deliveries | 8.5% (357 of 4,200 orders, June 2026)
Target late deliveries | 3.0%
Baseline mean lead time (hrs) | 32.8
Baseline std deviation (hrs) | 10.8
CTQ / promised lead time (hrs) | 48
Annualised COPQ (S$) | 1,674,000
Sponsor | Distribution Manager
Green Belt (project lead) | You
Team | Pick supervisor, Despatch lead, WMS analyst, Carrier liaison
Define tollgate | Week 2
Measure tollgate | Week 5
Analyze tollgate | Week 8
Improve tollgate | Week 12
Control / closure | Week 16
Notes
• Your problem statement must contain the process, the period, the measurable gap and the impact — and no cause or solution.
• Goal statement: reduce late deliveries from 8.5% to 3.0% by week 16.